# IGF 6 – Comms checklist/action paln v2

September 26-30 2011
General comms coordinator: Analía
On site comms coordinator : Grady

Area	Task	Responsible[1]	Comments	Update/deadline

Before the event
APC.org	Update project page on APC.org	Grady	http://www.apc.org/en/node/6924/	DONE
	Produce and disseminate APC's pre event and pre-events.	Grady	General info of APC at the IGF and pre-event in the three languages.	DONE
	Schedule	Grady	Spread sheet in a Google doc so people can edit and pdf online.	Google Doc done. PDF needs to be up. Deadline: Sept 7.
	Set up and maintain hotboxes promoting the event and key documents or other resources in all languages.	Analía	Done. Analía will update the three languages.	DONE
	Define person to sign off IGF documents before they go public	Analía		Done. Sign-off person is Valeria.
	Define translation criteria. We recommend only translating documents key to possible regional projects and not logistical information.	Analía	General info of APC at the IGF and pre-event in the three languages. Is there an IGF translation budget?	Email sent to team.
	Post info on remote participation.	Grady	Analía checking on CIPP list who is in charge. Grady to post info once it's available. Grady, pls check with members who is organising remote hubs. We also need contact details on remote moderators.	September 12.
	Follow up and post strategy brief (this includes APC's priorities and goals for the event).	Analia/Grady/Avri	Avri writing brief.	September 20.
	APC's assessment. Agree a timeline and and define responsibilities with the CIPP team.	Ani	This will be produced AFTER the IGF but we need to agree on a timeline beforehand.	Analía sent email to CIPP-list on Aug. 23. Valeria is following up.
	Produce communications strategy for the event	Analia/Grady	To be photocopied and circulated onsite to staff and members. Must include onsite contact info.	We will work on this as soon as the brief is done. Grady will be collecting contact details in the meantime.
Council, IGF and team lists.	Collect details (including email, mobile phone and Twitter accounts) of staff and members attending. / Collect details of events organised by members.	Grady	Using the IGF list	Sept. 12
Promotional materials	Coordination of printing and shipping	Analía/or Henrik	We may be able to print in Kenya. Check with ALIN. Analía checking with team what materials need to be printed.	Analía checking with team.
	Check with project coordinators what research needs to be disseminated and how would people like to do it (posters?)	Analia		Analía checking with team.
	GISW promotion including generating future orders	Kah	AE has suggested mail order forms. KAH is looking into print on demand.	Sept. 12
	Poster with GISW cover	Kah
Publications	APC office manager can coordinate the taking of materials to the event.	Analía to communicate with Eunice.	This includes checking which publications each staff have with them.	Sept. 12
Workshop preparation	Prepare handouts with mini-bios of the speakers of our events.	Grady	At least one different handout per workshop ready to be printed.	Sept 20
	Check with workshop organisers if they will need printouts for promoting specific events.	Grady	Sometimes it might be cheaper to print and photocopy at home.	Sept 12.
Logistics	Check if there will be a mini-printer.	Grady to liaise with Eunice.		Sept 7.
	Check if there is an “event toolbox” available. If not purchase one.	Grady	There should be: scissors, markers (thick and of different colours), scotch tape, duck tape, thread, papers of different colours. We need something where to print names of panelists too. / Joy also suggested a “white board poster”. Grady to find out.

At the event
Booth	Grady will coordinate the decoration of the booth :) You can use the stencil and the stickers we'll have. / Booth volunteer schedule – Produce mini schedule and coordinate the volunteers so there is someone always on the booth.	Grady		Onsite.
	Collect business cards. A little cardbox with “subscribe to APCNews” available on the booth.	Grady		Onsite.
Daily check-ins	Staff and members will have a daily check-in on site to coordinate the day's activities.	Grady	Grady to make sure that everyone knows where an when check-ins are taking place. The booth can be a good place to announce this.
	Info about our events with updated rooms and times should be displayed.	Grady	This might be in the form of a hand-made poster.
Comms outputs	Coordination of onsite comms strategy including blogging, tweeting and video interviews. (production needs to happen before)	Analia/Grady	Ani to produce strategy, Grady to oversee implementation. Remote support from comms team.
After the event
APC assessment	Production of assessment not more than 2 weeks after the event. Translation into three languages.	Valeria	We checked with Valeria and it should be ready to go on October 15.
[1] First person named is primary responsible.